## Por entregas
Dedication time
Work delivery: | Tasks: | Subtasks: | min: | hours:
1º | Organization | Role distribution | 120 | 2
|  | Benchmarking | 660 | 11
|  | Document creation (Overleaf) | 120 | 2
| Delivery writing | Format | 120 | 2
|  | Orthographic review | 120 | 2
|  | Abstract | 60 | 1
|  | Benchmark | 120 | 2
|  | Planning | 120 | 2
|  | Annexes (Minutes) | 90 | 1.5
| Gantt | List of tasks | 210 | 3.5
|  | Total | 210 | 3.5
|  | General & review | 90 | 1.5
| Others tasks | Budget | 120 | 2
|  | Contingencies | 180 | 3
|  | Meetings | 900 | 15
|  | Total: | 3240 | 54
2º | Delivery writing | Format | 120 | 2
|  | Orthographic review | 120 | 2
|  | Abstract | 45 | 0.75
|  | Technological exploration | 300 | 5
|  | Specifications | 300 | 5
|  | Annexes (Minutes) | 60 | 1
| Programming code | Sudoku segmentation | 360 | 6
|  | Sudoku Orientation | 360 | 6
|  | Grid identification | 720 | 12
|  | Number Recognition | 720 | 12
| Gantt | Reset planning | 30 | 0.5
| Others tasks | Budget | 60 | 1
|  | Shared platform (Github) | 60 | 1
|  | Meetings | 525 | 8.75
|  | Contingencies | 300 | 5
|  | Total: | 4080 | 68
Dedication time
Work delivery: | Tasks: | Subtasks: | min: | hours:
3º | Website design | Platform Search | 30 | 0.5
|  | Platform Recognition | 210 | 3.5
|  | Section identification | 60 | 1
|  | Editorial staff | 420 | 7
|  | Edition staff | 360 | 6
| Programming code | Sudoku segmentation | 300 | 5
|  | Sudoku Orientation | 300 | 5
|  | Grid identification | 600 | 10
|  | Number Recognition | 600 | 10
| Gantt | Reset planning | 30 | 0.5
| Others tasks | Meetings | 600 | 10
|  | Contingencies | 300 | 5
|  | Budget | 60 | 1
|  | Total: | 3870 | 64.5
4º | Delivery writing | Format | 120 | 2
|  | Orthographic review | 120 | 2
|  | Abstract | 30 | 0.5
|  | Introduction | 120 | 2
|  | App Structure | 240 | 4
|  | Results | 120 | 2
|  | Conclusions and future improvements | 120 | 2
|  | Annexes (Minutes) | 30 | 0.5
| Programming code | Sudoku segmentation | 60 | 1
|  | Sudoku Orientation | 480 | 8
|  | Grid identification | 300 | 5
|  | Number Recognition | 180 | 3
|  | Testing with different models | 300 | 5
|  | Sudoku Resolution | 300 | 5
|  | Code Unification | 600 | 10
| Gantt | Reset planning | 60 | 1
| Others tasks | Budget | 60 | 1
|  | Meetings | 900 | 15
|  | Contingencies | 600 | 10
|  | Total: | 4740 | 79
|  | Global Total: | 15930 | 265.5